## Meetings
BA | Scrum Master | Product owner
Daily Scrum | Daily Scrum |  | Daily Scrum
Pre-iteration planning | Pre-iteration planning |  | Pre-iteration planning
Iteration planning | Iteration planning |  | Iteration planning
Retrospection | Retrospection |  | Retrospection

## Process
Task | Summary | Frquency | Meeting | Example
Identify Project vision - Plan product backlog | Me along with Product Owner define the product planning for next few Sprint. We start with the new scope to be implemented in the application, Use cases to be converted to Epics, Estimate the timeline for the scope backlog, Resourcing etc | On Completion of Epic |  | Epic - Guidewire - Policy Creation User story - User management Sprint - Add new user, Edit user details For ex: In PBS application we recently planned to migrate from Legacy to modernization.
Requirement planning | Use cases, Epics, User Stories
Estimation
Sprint Planning | Don’t forget the main Scrum values. Keep sprints short and commit to an achievable number of user stories. Focus on one sprint at a time. Have the courage to break the release plan when absolutely necessary. Respect everyone’s perspective when choosing items and estimating scope | Every Thursday
Release planning

## Gantt Chart
|  | 2023 |  |  | 2024 | [7 empty] | Policy Creation
Policy Admin
August | September | October | November | December | January | February | March | April | May | June | July | August | Underwriting
Pod 1 - | [12 empty] | Rating
| Update pre-rating templates |  | Rating Release ver 13.1 |  | Rating release 14.0 | UAT migration | Underwriting Rules upgrade |  | Quote, Bind, Issue - API fixes |  | Underwriting pre-release | Pod 1 - | Quote, Bind, Issue
Renewal
Portfolio Business Services
Pod 2 -
|  | PBS - Splunk integration |  | PBS Release 16.1 | PBS Bolt upgrade |  | PBS - Billing migration |  | PBS - APIGEE | PBS - Unit testing | Pod 2 -

## Questions
| What are Scrum artifacts? | There are three Scrum artifacts: the product backlog, the sprint backlog, and the product increment
| What are the limitations of Scrum? | Scrum is generally recommended for teams or industries that expect to face change. Because they are designed to adapt quickly and operate in short cycles, Scrum teams are generally small, making it hard for pure Scrum to work for projects with large teams without some modifications.
Product Planning
| What is a User story? | A user story is a short, simple description of a feature or functionality that a user or customer would like to see in an application. User stories are typically used in agile software development as a way to capture requirements from customers or users.
How to write use cases?
BRD, FRD
| Why should we use user stories instead of functional requirements? | User stories are a more user-centric way of thinking about the requirements for a project. They focus on what the user needs and wants from the system, rather than on the specific functions that the system needs to perform. This can help to ensure that the final product is more user-friendly and intuitive.
| What are acceptance criteria and how can they be used with user stories? | Acceptance criteria are the specific conditions that a software product must meet in order to be accepted by the customer. They are often used in conjunction with user stories, which are brief descriptions of a feature from the perspective of the user. By including acceptance criteria with user stories, developers can be sure that they are building the product the customer wants.
| How do you calculate the capacity and velocity of a Scrum team? | Velocity is calculated by averaging the number of completed story points in previous sprints. Velocity is used to determine the capacity—how many product backlog items the team should take for the next sprint. Capacity shows how much availability the team has for the upcoming sprint. Other things held constant, the capacity should be equal to the velocity. However, a few factors can lower the capacity: Vacations Sick days Onboarding of new team members Other ad hoc company events or meetings
Defects | How do you manage defects in agile? | Not all defects are created equal. Some may have a critical impact on the functionality, usability, or security of the product, while others may be minor or cosmetic. Agile teams should prioritize and categorize defects based on their severity, urgency, and business value. This helps to decide which defects need to be fixed immediately, which can be deferred to a later sprint or release, and which can be ignored or closed.
| What will you to if there is a Production defect leakage | RCA
Defect Triage meeting
| What is user story mapping? | User story mapping represents and arranges user stories that help with understanding system functionalities, system backlog, planning releases, and providing value to customers. They arrange user stories based on their priority on the horizontal axis. On the vertical axis, they are represented based on the increasing levels of sophistication.
| How are user stories, epics, and tasks different? | User Stories: They provide the team with simple explanations of the business’ requirements created from the end user's perspective. Epics: An epic is a collection of related user stories. They are usually large and complex. Tasks: Tasks are used to break down user stories further. They’re the smallest unit in Scrum that is used to track work. A person or a team of two people usually work on a task.
| What is a Sprint? | Sprint is a terminology used in Scrum, used to describe a time-boxed iteration. During a sprint, a specific module or feature of the product is created. The duration of a sprint can vary between a week or two.
| What is Velocity? | Velocity is a metric used to measure the amount of work completed by a team during a sprint. It refers to the number of user stories completed in a sprint.
| How is Estimation Done in a Scrum Project? | The estimation of user stories is done based on their difficulty A particular scale is used to assess the difficulty of the user stories. Some type of scales are: Fibonacci Series (1, 2, 3, 5, 8…)
| What are some risks in Scrum? How are they handled? | Budget: The risk of exceeding budgets People (team): Team members need to be of appropriate skill and capability Sprint (duration and deliverables): Exceeding the duration, addition of the scope of work Product (user stories, epics): Having ill-defined user stories and epics Knowledge and capability: Having the appropriate resources
How do you define a storyboard in agile?
| How does a Scrum Master track Sprint progress? | Daily Scrum meetings Scrum retrospectives Sprint planning Escaped defects Defect density Sprint burndown Team velocity
How to Prioritize the backlog?
How do you determine the velocity of a sprint in a scrum?
Challenges as Scrum master?
Which abilities do you believe are critical for a scrum master to possess?
How to prioritizes the backlog items?
| What is a Burnup and Burndown Chart? | A burnup chart is a tool that’s used to track the amount of work that’s been completed and to represent the total amount of work that needs to be done for a sprint/project. A burndown chart represents how fast working through user stories is. It shows total effort against the amount of work for each iteration.
| What happens in Sprint Retrospectives? | The sprint retrospective takes place after the sprint review. During this meeting, past mistakes, potential issues, and new methods to handle them are discussed. This data is incorporated into the planning of a new sprint.
Can you define a release candidate?
How you do Release planning?
What if the Release is rolled back?
What are some negatives of using scrum?
What are the benefits of using scrum?
How much time do you usually devote to planning your tasks as a scrum master?
How is a burnup chart different from a burndown chart?
| What's the distinction between agile and scrum? | One of the major distinctions is that scrum concentrates on dividing the assignment into manageable and continuous sprint time periods. Scrum is also a more team-oriented methodology with a scrum master who ensures that their team has access to all the assets necessary to accomplish an assignment, while agile has a project manager that leads the team. I've gained experience working in both agile and scrum settings. I prefer scrum because it enables me to interact more closely with my team and allows for feedback from each member on the best strategy to complete the work."

## Team
Sprint | Q4 11/13 - 11/24 | Sprint | Q4 11/13 - 11/24
Developers | 4 | Developers | 7
Testers | 2 | Testers | 3
Story points per Sprint | 60-70 | Story points per Sprint | 120
QA Story points | 20 | QA Story points | 30

## Product - Sprint
How are the Product and Sprint Backlog different from One Another?
| Product Backlog | Sprint Backlog
| It is a list of items that need to be completed for developing the product | It is a list of items to be completed during each sprint
| The backlog is collected from the customer by the product owner and assigned to the team | The team collects the backlog from the product owner and sets up the time frame for the sprint
| It has a specific end goal | It is specific to a sprint
| Based on customer vision | Can vary based on product vision defined by the product owner
| It’s independent of the sprint backlog | It’s dependant on the product backlog
| The product owner maintains the backlog until the project is complete | Each new sprint has backlogs added by the team
| What is a User Story? | A user story is an agile software development/ project management tool that provides teams with simple, natural language explanations of one or more features of the project that’s written from the perspective of the end-user. The user story doesn’t go into detail but only mentions how certain types of work will bring value to the end-user. The end-user, in this case, could be an external component or an internal customer/colleague within the organization. They also form the building block of agile frameworks like epics and other initiatives. They ensure that the teams work towards the goals of the organization, with the help of epics and initiatives. The requirements to make a user story a reality are added later, after discussions with the team. They are recorded on post-it notes, index cards, or project management software.