## Meetings
BA | Scrum Master | Product owner
Daily Scrum | Daily Scrum |  | Daily Scrum
Pre-iteration planning | Pre-iteration planning |  | Pre-iteration planning
Iteration planning | Iteration planning |  | Iteration planning
Retrospection | Retrospection |  | Retrospection

## Process
Task | Summary | Frquency | Meeting | Example
Identify Project vision - Plan product backlog | Me along with Product Owner define the product planning for next few Sprint. We start with the new scope to be implemented in the application, Use cases to be converted to Epics, Estimate the timeline for the scope backlog, Resourcing etc | On Completion of Epic |  | Epic - Guidewire - Policy Creation User story - User management Sprint - Add new user, Edit user details For ex: In PBS application we recently planned to migrate from Legacy to modernization.
Requirement planning | Use cases, Epics, User Stories
Estimation | Estimations are basically done during Sprint planning. The objective is to consider the User Stories for the Sprint by Priority and by the Ability of the team to deliver during the Time Box of the Sprint (2 weeks) Estimations done through Planning Poker method using the Fibonacci sequence (1, 2, 3, 5, 8, 13, 21…) for story cards for the iteration.
Sprint Planning | Don’t forget the main Scrum values. Keep sprints short and commit to an achievable number of user stories. Focus on one sprint at a time. Have the courage to break the release plan when absolutely necessary. Respect everyone’s perspective when choosing items and estimating scope | Every Thursday
Release planning

## Questions
Example
| What are Scrum artifacts? | There are three Scrum artifacts: the product backlog, the sprint backlog, and the product increment
| What are the limitations of Scrum? | Scrum is generally recommended for teams or industries that expect to face change. Because they are designed to adapt quickly and operate in short cycles, Scrum teams are generally small, making it hard for pure Scrum to work for projects with large teams without some modifications.
Product Planning
| What is a User story? | A user story is a short, simple description of a feature or functionality that a user or customer would like to see in an application. User stories are typically used in agile software development as a way to capture requirements from customers or users.
How to write use cases?
BRD, FRD
| Why should we use user stories instead of functional requirements? | User stories are a more user-centric way of thinking about the requirements for a project. They focus on what the user needs and wants from the system, rather than on the specific functions that the system needs to perform. This can help to ensure that the final product is more user-friendly and intuitive.
| What are acceptance criteria and how can they be used with user stories? | Acceptance criteria are the specific conditions that a software product must meet in order to be accepted by the customer. They are often used in conjunction with user stories, which are brief descriptions of a feature from the perspective of the user. By including acceptance criteria with user stories, developers can be sure that they are building the product the customer wants.
| Sprint backlog - process | 1. Cards will be assigned by the Scrum master for Dev and QA 2. Dev team will complete the cards, do the unit test and move them for Ready for testing 3. Testing team will start picking the cards from Ready for testing queue 5. If there is any defect then QA team will check with Dev team and raise the Defect linking it to the reqruirement and the Card 4. QA team will complete the testing and mark the card as Done and move it for Sign-off 6. Every week Scrum master, Dev lead, QA lead will have Iteration meeting to discuss the Sprint progress and make sure tehre are no blockers, if the cards are spilled over they will plan to complete the Critical/Priority cards in the current sprint and move the reamining to the next sprint as new backlog
| What is Entry and Exit Criteria in STLC? | Entry Criteria: Entry Criteria gives the prerequisite items that must be completed before testing can begin. Exit Criteria: Exit Criteria defines the items that must be completed before testing can be concluded You have Entry and Exit Criteria for all levels in the Software Testing Life Cycle (STLC) In an Ideal world, you will not enter the next stage until the exit criteria for the previous stage is met. But practically this is not always possible. So for this tutorial, we will focus on activities and deliverables for the different stages in STLC life cycle. Let’s look into them in detail.
| how to define proper entry exit criteria? | For an agile project, let’s say we want to have exit criteria in place for the end of the sprint. We will need to work on defining them at the beginning of the sprint, or at the release-planning stage. Once the activity begins, the goal is to achieve all exit criteria by the end. Exit criteria for a sprint should be defined based on the tasks, user stories, features, and work units in the sprint, at a generic level. Here are some examples of sprint-level exit criteria: All user stories in the sprint backlog must be completed (see next section) All design tasks and special tasks picked for the sprint must be completed No critical issues must be open Regression testing of all features developed in all previous sprints must be executed The automated regression test suite must be executed at least once with no issues
Defects | How do you manage defects in agile? | Not all defects are created equal. Some may have a critical impact on the functionality, usability, or security of the product, while others may be minor or cosmetic. Agile teams should prioritize and categorize defects based on their severity, urgency, and business value. This helps to decide which defects need to be fixed immediately, which can be deferred to a later sprint or release, and which can be ignored or closed.
| What will you to if there is a Production defect leakage | 1. Scrum master/PO will request for a Root cause analysis to identify the cause of defect, if it is an env issue, QA miss or test data issue 2. It's the Product Owner's job to inform the team about its priority by ordering it in the backlog. 3. The development team will pick it into the next or current sprint 4. If there is a gap in the test coverage QA team will add the new test cases as part of coverge gap. 5. Thorough unit testing and regression testing will be done to make sure no more prod def leakage
| How to prevent Prod defect leakage? | 1. A thorough unit testing should be carried out 2. Proper entry exit criteria on requirements 3. Greater than 85% of Test coverage. Use Hexawise tool for increasing test coverage 4. Use automation tools to run Smoke test to quick identification of bugs 5. Proper regression testing covering End to end scenarios
Defect Triage meeting
| What is user story mapping? | User story mapping represents and arranges user stories that help with understanding system functionalities, system backlog, planning releases, and providing value to customers. They arrange user stories based on their priority on the horizontal axis. On the vertical axis, they are represented based on the increasing levels of sophistication.
| How are user stories, epics, and tasks different? | User Stories: They provide the team with simple explanations of the business’ requirements created from the end user's perspective. Epics: An epic is a collection of related user stories. They are usually large and complex. Tasks/cards: Tasks are used to break down user stories further. They’re the smallest unit in Scrum that is used to track work. A person or a team of two people usually work on a task.
| What is a Sprint? | Sprint is a terminology used in Scrum, used to describe a time-boxed iteration. During a sprint, a specific module or feature of the product is created. The duration of a sprint can vary between a week or two.
| What is Velocity? | Velocity is a metric used to measure the amount of work completed by a team during a sprint. It refers to the number of user stories completed in a sprint.
| How do you calculate the capacity and velocity of a Scrum team? | Velocity is calculated by averaging the number of completed story points in previous sprints. Velocity is used to determine the capacity—how many product backlog items the team should take for the next sprint. For instance, if the Scrum Team has finished a total of 80 points over 4 Sprints then the actual velocity of the team would be 20 points per Sprint. Capacity shows how much availability the team has for the upcoming sprint. Other things held constant, the capacity should be equal to the velocity. However, a few factors can lower the capacity: Vacations Sick days Onboarding of new team members Other ad hoc company events or meetings
| How is Estimation Done in a Scrum Project? | Estimations are basically done during Sprint planning. The objective is to consider the User Stories for the Sprint by Priority and by the Ability of the team to deliver during the Time Box of the Sprint (2 weeks) Estimations done through Planning Poker method using the Fibonacci sequence (1, 2, 3, 5, 8, 13, 21…) for story cards for the iteration.
| What are some risks in Scrum? How are they handled? | Budget: The risk of exceeding budgets People (team): Team members need to be of appropriate skill and capability Sprint (duration and deliverables): Exceeding the duration, addition of the scope of work Product (user stories, epics): Having ill-defined user stories and epics Knowledge and capability: Having the appropriate resources
| How do you define a storyboard in agile? | Scrumboard or storyboard is the place where team keeps track of these work items. A storyboard canbe a simple physical board where user stories are marked on sticky notes so team can easily move a note from “todo” to “in progress”or “done” column. Agile project management tools are also used quite widely for keeping record of all user stories and their current status.
| How does a Scrum Master track Sprint progress? | Daily Scrum meetings Scrum retrospectives Sprint planning Escaped defects Defect density Sprint burndown Team velocity
How to Prioritize the backlog?
Challenges as Scrum master?
How to prioritizes the backlog items?
| What is a Burnup and Burndown Chart? | A burnup chart is a tool that’s used to track the amount of work that’s been completed and to represent the total amount of work that needs to be done for a sprint/project. A burndown chart represents how fast working through user stories is. It shows total effort against the amount of work for each iteration.
| What happens in Sprint Retrospectives? | The sprint retrospective takes place after the sprint review. During this meeting, past mistakes, potential issues, and new methods to handle them are discussed. This data is incorporated into the planning of a new sprint.
How you do Release planning?
What are some negatives of using scrum?
What are the benefits of using scrum?
How much time do you usually devote to planning your tasks as a scrum master?
How is a burnup chart different from a burndown chart?
| What's the distinction between agile and scrum? | One of the major distinctions is that scrum concentrates on dividing the assignment into manageable and continuous sprint time periods. Scrum is also a more team-oriented methodology with a scrum master who ensures that their team has access to all the assets necessary to accomplish an assignment, while agile has a project manager that leads the team. I've gained experience working in both agile and scrum settings. I prefer scrum because it enables me to interact more closely with my team and allows for feedback from each member on the best strategy to complete the work."
Scenario based questions
| Factors to be considerd for a feature to be released to production. Release plan pre-requisites. | 1. Entry exit criteria is met for development and testing 2. Unit testing - Sign off 3. UAT - Sign off (Regression testing + Automation testing execution + Performance testing) 5. Prepare reelase - Implementation - approval 6. Test in Dark environment; 7. Deployment successful
What if the deivery of the product is beyond the timeline/schedule?
What happens when the release is called off due to UAT defect or issue?
| What is the average story points per resource in 1 Sprint? | 10
| Can you define a release candidate? | 1. Entry exit criteria is met for development and testing 2. Unit testing - Sign off 3. UAT - Sign off (Regression testing + Automation testing execution + Performance testing) 5. Prepare reelase - Implementation - approval 6. Test in Dark environment; 7. Deployment successful
The team constantly struggles at the beginning of every Sprint because their Product Backlog is empty and the Product Owner doesn’t have time to update it. They waste time getting the information from him. What do you do?
| Your team’s velocity has been gradually decreasing in the past few Sprints, but they have not mentioned any issues to you. Should you be concerned? | Decreasing velocity may be an indication of a problem, but it might not be. For example, if the team is getting more accustomed to the product, and more confident when working with it, their estimates would tend to go down, which could show decreasing velocity. But there also might be some external dependencies that prevent the team from completing the same amount of work as before. Of even, something natural reasons. Like during a flu season where many team members may be getting sick all at the same time. SO my approach would be first figure out what’s wrong. In addition, I wouldn’t be as concerned with velocity itself – this is really just a metric to help the team plan. It doesn’t really represent value or team performance. It may be more useful to look at some other metrics like cycle time, number of defects, team health index, and more
The team has been complaining about the Daily Scrum being a waste of time. It’s practically Product Owner and Team Lead talking to each other for 30 minutes. What’s your approach?

## Release flow
| EC2.0 | Insurance Guidewire - Policy Center
| Business Owners | Commercial Auto | Commercial Property | In land Marine | Workers compensation
Epics | Third-party liability | Comprehensive Coverage |  |  |  | effective claims management
severe claims identification
subrogation recovery
User Stories | create insurance policies | adjust claims | generate reports |  |  | claims analysis
Sprints | FNOL (First notice of Loss) | Subrogation recovery
Releases | FNOL | Subrogation recovery

## Gantt Chart
|  | 2023 |  |  | 2024 | [7 empty] | Policy Creation
Policy Admin
August | September | October | November | December | January | February | March | April | May | June | July | August | Underwriting
Pod 1 - | [12 empty] | Rating
| Update pre-rating templates |  | Rating Release ver 13.1 |  | Rating release 14.0 | UAT migration | Underwriting Rules upgrade |  | Quote, Bind, Issue - API fixes |  | Underwriting pre-release | Pod 1 - | Quote, Bind, Issue
Renewal
Portfolio Business Services
Pod 2 -
|  | PBS - Splunk integration |  | PBS Release 16.1 | PBS Bolt upgrade |  | PBS - Billing migration |  | PBS - APIGEE | PBS - Unit testing | Pod 2 -

## Team
Sprint | Q4 11/13 - 11/24 | Sprint | Q4 11/13 - 11/24
Developers | 4 | Developers | 7
Testers | 2 | Testers | 3
Story points per Sprint | 60-70 | Story points per Sprint | 120
QA Story points | 20 | QA Story points | 30

## Product - Sprint
How are the Product and Sprint Backlog different from One Another?
| Product Backlog | Sprint Backlog
| It is a list of items that need to be completed for developing the product | It is a list of items to be completed during each sprint
| The backlog is collected from the customer by the product owner and assigned to the team | The team collects the backlog from the product owner and sets up the time frame for the sprint
| It has a specific end goal | It is specific to a sprint
| Based on customer vision | Can vary based on product vision defined by the product owner
| It’s independent of the sprint backlog | It’s dependant on the product backlog
| The product owner maintains the backlog until the project is complete | Each new sprint has backlogs added by the team
| What is a User Story? | A user story is an agile software development/ project management tool that provides teams with simple, natural language explanations of one or more features of the project that’s written from the perspective of the end-user. The user story doesn’t go into detail but only mentions how certain types of work will bring value to the end-user. The end-user, in this case, could be an external component or an internal customer/colleague within the organization. They also form the building block of agile frameworks like epics and other initiatives. They ensure that the teams work towards the goals of the organization, with the help of epics and initiatives. The requirements to make a user story a reality are added later, after discussions with the team. They are recorded on post-it notes, index cards, or project management software.

## Jira
Scenarios to try in Jira | https://premieragile.com/how-to-use-the-atlassian-jira-tools-for-scrum-teams/
Create a Scrum project
Make tasks and user stories in the backlog
Creating a sprint
Move the user stories to next Sprint
Map the requirements to Tasks/user stories
Create a Bug
Create burndown chart
Closing sprints and getting reports
Using filters to find the issues you need
Organizing and structuring the Product Backlog
Creating a timeline or a roadmap
Kanban basics - how Jira treats Kanban boards and how you can use them for non-Scrum related work